SECTION 013216 – CONSTRUCTION SCHEDULE

- GENERAL

      - SUMMARY

        - This Section consists of Construction Schedule requirements including but not limited to the following:

Adjust list below to suit Project.

          - Schedule of Values

          - Construction Schedule Requirements.

          - Construction Schedule Updates.

          - Time Impact Analysis.

        - Purpose:  The purpose of the Construction Schedule is to ensure adequate planning, coordination, scheduling, and reporting during execution of the work by the Contractor.  The Construction Schedule will assist the Contractor and Contracting Officer in monitoring the progress of the work, evaluating proposed changes, and processing the Contractor's monthly progress payment

      - DEFINITIONS

        - Activity:  A discrete part of a project that can be identified for planning, scheduling, monitoring, and controlling the construction project.  Activities included in a construction schedule consume time and resources.

          - Critical activities are activities on the critical path.  They must start and finish on the planned early start and finish times.

          - Predecessor Activity:  An activity that precedes another activity in the network.

          - Successor Activity:  An activity that follows another activity in the network.

        - Cost Loading:  The allocation of the Schedule of Values for the completion of an activity as scheduled.  The sum of costs for all activities must equal the total Contract Sum, unless otherwise approved by the Contracting Officer.

        - CPM:  Critical path method, which is a method of planning and scheduling a construction project where activities are arranged based on activity relationships.  Network calculations determine when activities can be performed and the critical path of Project.

        - Critical Path:  The longest connected chain of interdependent activities through the network schedule that establishes the minimum overall Project duration and contains no float.

        - Float:  The measure of leeway in starting and completing an activity.

          - Float:  Float is not for the exclusive use or benefit of either the Government or the Contractor but is jointly owned.

          - Free float is the amount of time an activity can be delayed without adversely affecting the early start of the successor activity.

          - Total float is the measure of leeway in starting or completing an activity without adversely affecting the planned Project completion date.

        - Resource Loading:  The allocation of manpower and equipment necessary for the completion of an activity as scheduled.

        - Fragnet:  A partial or fragmentary network that breaks down activities into smaller activities for greater detail.

      - SUBMITTALS

Retain or delete paragraph below based on the requirement for either a Schedule of Values or a Cost Loaded Schedule.

        - Schedule of Values: After contract award and before the Pre-Construction conference submit a schedule of dollar values based on the Contract Price Schedule.

        - Construction Schedule: After contract award and before the Pre-Construction conference, submit [two] <Insert number> copies of initial schedule, large enough to show entire schedule for entire construction period.

          - Submit an electronic copy of schedule, in the software it was created in, on CD-R, and labeled Initial schedule with date.

        - CPM Reports:  Concurrent with CPM schedule, submit [three] <Insert number> copies of each of the following computer-generated reports.  Format for each activity in reports shall contain activity number, activity description, [cost] and resource loading, original duration, remaining duration, early start date, early finish date, late start date, late finish date, and total float in calendar days.

          - Activity Report:  List of all activities sorted by activity number and then early start date, or actual start date if known.

          - Logic Report:  List of predecessor and successor tasks for all activities, sorted in ascending order by activity number and then early start date, or actual start date if known.

          - Total Float Report:  List of all activities sorted in ascending order of total float.

        - Construction Schedule Updates:  On or before the 7th day preceding the progress payment request date, submit estimates of the percent completion of each schedule activity and necessary supporting data.  Provide two paper copies and one electronic copy.

        - Construction Schedule Revisions and Time Impact Analysis: For each Construction Schedule revision submit one electronic copy and [two] <Insert Number>paper copies of a Time Impact Analysis. Each Time Impact Analysis shall include a Fragmentary Network (Fragnet) demonstrating how the Contractor proposes to incorporate a modification, change, delay, or Contractor request into the Construction Schedule.

      - QUALITY ASSURANCE

        - The Contractor shall meet with the Contracting Officer on the day of the preconstruction conference to go over the following:

Some or most of these review topics should already have been covered before this meeting. Comments should have been generated and sent to the contractor. The primary focus of this meeting should be dealing with outstanding issues, incorporation of comments and the timing for receipt of an acceptable baseline schedule.

          - Review software limitations, content and format for reports.

          - Verify availability of qualified personnel needed to develop and update schedule.

          - Discuss constraints, including [phasing] [work stages] [area separations] [interim milestones] [and] [partial Government occupancy].

          - Review delivery dates for Government-furnished products.

          - Review schedule for work of separate Government contracts.

          - Review time required for review of submittals and re-submittals.

          - Review requirements for tests and inspections by independent testing and inspecting agencies.

          - Review time required for completion and startup procedures.

          - Review and finalize list of construction activities to be included in schedule.

          - Review initial schedule comments, resolve issues and progress on incorporating them

          - Review procedures for updating schedule.

        - Contractor's Schedule Representative:  Before or at the preconstruction conference, designate in writing and provide the qualifications of an authorized representative in the Contractor's organization who shall be responsible for coordinating with the Contracting Officer during the preparation and maintenance of the Construction Schedule.

      - COORDINATION

        - Coordinate preparation and processing of schedules and reports with performance of construction activities and with scheduling and reporting of separate contractors.

        - Coordinate Construction Schedule with the Schedule of Values, list of subcontracts, Submittals Schedule, progress reports, payment requests, and other required schedules and reports.

          - In developing the Construction Schedule, ensure that subcontractor work at all tiers, as well as the prime contractor’s work, is included and coordinated in the Construction Schedule.

          - Secure time commitments for performing critical elements of the Work from parties involved.

          - Coordinate each construction activity in the network with other activities and schedule them in proper sequence.

- PRODUCTS

Retain paragraph and subparagraphs below if a Schedule of Values is required and a Cost Loaded Schedule is not.

      - SCHEDULE OF VALUES

        - Breakdown each lump-sum item into component parts of work for which progress payments may be requested. The total costs for the component parts of work shall equal the contract price for that lump-sum item. The Contracting Officer may request data to verify accuracy of dollar values. Include mobilization, general condition costs, overhead and profit in the total dollar value of unit price items and in the component parts of work for each lump-sum item. Do not include mobilization, general condition costs, overhead or profit as a separate item.

        - Do not break down unit price items. Use only the contract price for unit price items.

        - The total cost of all items shall equal the contract price. The Schedule of Values will form the basis for progress payments.

        - An acceptable Schedule of Values shall be agreed upon by the Contractor and Contracting Officer before the first progress payment is processed.

      - CONSTRUCTION SCHEDULE REQUIREMENTS

        - Construction Schedule:  Prepare Construction Schedule using a computerized, [cost], [and] resource-loaded, time-scaled CPM network analysis diagram for the Work.

          - Develop and finalize Construction Schedule so it can be accepted for use no later than [30] <Insert number> days after date established for the Notice of Award.

            - Failure to include any work item required for performance of this Contract shall not excuse Contractor from completing all work within applicable completion dates, regardless of Governments acceptance of the schedule.

          - Establish procedures for monitoring and updating Construction Schedule and for reporting progress.  Coordinate procedures with progress meeting and payment request dates.

          - Use "one workday" as the unit of time. Incorporate nonworking days and government holidays into the schedule.

        - Construction Schedule Preparation:  Prepare a list of all activities required to complete the Work.  Using the preliminary CPM network diagram, prepare a skeleton network to identify probable critical paths.

          - Activities:  Indicate the estimated duration, sequence requirements, and relationship of each activity in relation to other activities.

          - Critical Path Activities:  Identify critical path activities, including those for interim completion dates.  Scheduled start and completion dates shall be consistent with Contract milestone dates.

          - Processing:  Process data to produce output data on a computer-drawn, time-scaled network.  Revise data, reorganize activity sequences, and reproduce as often as necessary to produce the CPM schedule within the limitations of the Contract Time.

          - The Construction Schedule as developed shall show the sequence and interdependence of activities required for complete performance of the work.  Ensure all work sequences are logical and the Construction Schedule shows a coordinated plan of the work.

          - Resource loading of each activity shall include all personnel by labor category and equipment type and capacity proposed to complete the activity in the duration shown.

          - Time Frame: Proposed duration assigned to each activity shall be the Contractor's best estimate of time required to complete the activity considering the scope and resources planned for the activity.

            - The late finish date shown on the schedule shall be the same date as the last day of the contract period.

            - Contract completion date shall not be changed by submission of a schedule that shows an early completion date.

            - The Contractor shall limit use of lead or lag duration’s between schedule activities.

Revise first subparagraph below to suit Project.  Long activity durations provide less detail and, therefore, less information with which to manage a project.  As an alternative to specifying activity duration, indicate minimum and maximum number of activities, which will result in a similar effect.

            - Activity Duration:  Define activities so no activity is longer than [15] <Insert number> days, except for non-construction activities including mobilization, shop drawings and submittals, fabrication and delivery of materials and equipment.

            - Procurement Activities:  Include procurement process activities for the following long lead items and major items, requiring a cycle of more than 60 days, as separate activities in schedule.  Procurement cycle activities include, but are not limited to, submittals, approvals, purchasing, fabrication, and delivery.

              - <Insert list of major items or pieces of equipment.>

            - Submittal Review Time:  Include review and re-submittal times indicated. Coordinate submittal review times in Construction Schedule.

            - Startup and Testing Time:  Include not less than <Insert number> days for startup [and] testing [and commissioning activities].

            - Substantial Completion:  Allow time for Government administrative procedures necessary for certification of Substantial Completion.

          - Constraints:  Include constraints and work restrictions indicated in the Contract Documents and as follows in schedule, and show how the sequence of the Work is affected.

Delete subparagraphs below not applicable.

            - Phasing:  Arrange list of activities on schedule by phase.

            - Work under More Than One Contract:  Include a separate activity for each contract.

            - Work Restrictions:  Show the effect of the following items on the schedule:

Revise list below to suit Project.

              - Coordination with existing construction.

              - Limitations of continued occupancies.

              - Uninterruptible services.

              - Partial occupancy before Substantial Completion.

              - Use of premises restrictions.

              - Provisions for future construction.

              - Seasonal variations.

              - Environmental control.

            - Work Stages:  Indicate important stages of construction for each major portion of the Work.

            - Other Constraints:  <Insert additional constraints not indicated elsewhere.>

          - Milestones:  Include milestones indicated in the Contract Documents in schedule, including, but not limited to, the Notice to Proceed, Substantial Completion, and Final Completion[.] [, and the following interim milestones:]

            - <Insert additional milestones not indicated elsewhere.>

        - Joint Review, Revision, and Acceptance:

          - Within seven calendar days of receipt of the Contractor's proposed Construction Schedule, the Contracting Officer and Contractor shall meet for joint review, correction, or adjustment of the initial Construction Schedule.  Any areas which, in the opinion of the Contracting Officer, conflict with timely completion of the project shall be subject to revision by the Contractor.

          - Within seven calendar days after the joint review between the Contractor and Contracting Officer, the Contractor shall revise and resubmit the Construction Schedule in accordance with agreements reached during the joint review.

          - In the event the Contractor fails to define any element of work, activity, or logic, and the Contracting Officer review does not detect this omission or error, such omission or error, when discovered by the Contractor or Contracting Officer, shall be corrected by the Contractor within seven calendar days and shall not affect the contract time.

          - Upon acceptance of the Construction Schedule by the Contracting Officer, the Construction Schedule will be used to evaluate the Contractor's monthly applications for payment based upon information developed at the monthly Construction Schedule update meeting.

Retain the following paragraph and sub paragraphs if a cost loaded schedule is required and a Schedule of Values is not.

        - Cost Correlation:  In the heading of the schedule, provide a cost correlation line, indicating planned and actual costs.  On the line, show dollar volume of the Work performed as of dates used for preparation of payment requests.

          - Contractor shall assign cost to construction activities on the Construction Schedule. Costs shall not be assigned to submittal activities unless specified otherwise but may, with Contracting Officer’s approval, be assigned to fabrication and delivery activities.  Costs shall be included for testing and commissioning activities, operation and maintenance manuals, punch list activities, Project Record Documents, and demonstration and training (if applicable).

          - Each activity cost shall reflect an accurate value based on the Contract Price Schedule.

          - Total cost assigned to activities shall equal the total Contract Price.

        - Computer Software:  Prepare schedules using a program that has been developed specifically to manage construction schedules.

          - Software: The software shall be the latest version of [Primavera Project Planner], version <Insert designation>, [Primavera Contractor], version <Insert designation>, [Microsoft Project], version <Insert designation> or approved equal.

If a copy of the software is needed insert the following paragraph.

          - The Contractor shall provide to the Contracting Officer a licensed copy of the software used to create the Construction Schedule and a software reference manual.  The software and reference manual will be returned to the Contractor at completion of the Contract

- EXECUTION

      - CONSTRUCTION SCHEDULE UPDATES

        - Progress Meeting Updates: Provide updated schedule information before each weekly progress meeting.

          - Issue updated schedule concurrently with the report of each such meeting. Incorporate revisions into the schedule in a timely manner.

        - Monthly Schedule Updates:

          - General:  Update the Construction Schedule on a monthly basis to reflect actual construction progress and activities throughout the entire contract period and until project substantial completion. The status date of each schedule update shall be the 7th day preceding the progress payment request date.

          - Procedure:  The Contractor shall meet with the Contracting Officer each month at a Construction Schedule update meeting to review actual progress made through the status date of the Construction Schedule update, including dates activities were started and/or completed and the percentage of work completed on each activity started and/or completed.

          - Reports: Concurrent with making revisions to schedule, prepare tabulated reports showing the following:

Edit report requirements according to preferences.

            - Identification of activities that have changed.

            - Changes in early and late start dates.

            - Changes in early and late finish dates.

            - Changes in activity durations in workdays.

            - Changes in the critical path.

            - Changes in total float or slack time.

            - Changes in the Contract Time.

          - As the Work progresses, indicate Actual Completion percentage for each activity.

          - Progress Payments:  The monthly updating of the Construction Schedule shall be an integral part of the process upon which progress payments will be made under this contract.  If the contractor fails to provide schedule updates or revisions, then a portion of his monthly payment may be retained until such corrections have been made.

        - Distribution:  Distribute copies of accepted schedule to Contracting Officer, Contracting Officers Representative, Construction Management Representative, Subcontractors, testing and inspecting agencies, and other parties identified by Contractor with a need-to-know schedule responsibility.

          - Post copies in Project meeting rooms and temporary field offices.

          - When revisions are made, distribute updated schedules to the same parties and post in the same locations.  Delete parties from distribution when they have completed their assigned portion of the Work and are no longer involved in performance of construction activities.

        - Construction Schedule Revisions:

          - Required Revisions:  If, as a result of the monthly schedule update, it appears the Construction Schedule no longer represents the actual prosecution and progress of the work, the Contracting Officer will request, and the Contractor shall submit, a revision to the Construction Schedule.  The Contractor may also request reasonable revisions to the Construction Schedule in the event the Contractor's planning for the work is revised.  If the Contractor desires to make changes in the Construction Schedule, the Contractor shall notify the Contracting Officer in writing, stating the reason for the proposed revision.  Accepted revisions will be incorporated into the Construction Schedule at the next monthly schedule update.

          - Procedure:  If revision to the Construction Schedule is contemplated, the Contractor or Contracting Officer shall so advise the other in writing at least seven calendar days prior to the next monthly schedule update meeting, describing the revision and reasons for the revision. Government-requested revisions to the Construction Schedule will be presented in writing to the Contractor, who shall respond in writing within seven calendar days.

      - TIME IMPACT ANALYSIS FOR CONTRACT MODIFICATIONS CHANGES DLAYS AND CONTRACTOR REQUESTS:

          - Requirements:  When contract modifications or changes are initiated, delays are experienced, or the Contractor desires to revise the Construction Schedule, the Contractor shall submit to the Contracting Officer a written time impact analysis illustrating the influence of each modification, change, delay, or Contractor request on the contract time.

          - Time Extensions:  Activity delays shall not automatically mean that an extension of the contract time is warranted or due the Contractor.  It is possible that a modification, change, or delay will not affect existing critical path activities or cause non-critical activities to become critical.  A modification, change, or delay may result in only absorbing a part of the available total float that may exist within an activity chain of the Construction Schedule, thereby not causing any effect on the contract time.  Time extensions will be granted in accordance with the terms of the contract.

          - Extension of the contract time will be granted only to the extent the equitable time adjustments to the activity or activities affected by the modification, change, or delay exceeds the total (positive or zero) float available on a particular activity.

          - Procedure:  Each time impact analysis shall be submitted within the time period stated in a request for proposal, or the time period designated under the clauses entitled Changes or Default.  In cases where the Contractor does not submit a written request for extension of time and a time impact analysis within the designated time, it is mutually agreed that the particular modification, change, delay, or Contractor request does not require an extension of the contract time.  Upon acceptance, the time impact analysis shall be incorporated into the Construction Schedule at the next monthly schedule update.

          - Contract Modifications:  For each proposed contract modification and concurrent with its submission, prepare a time-impact analysis using fragnets to demonstrate the effect of the proposed change on the overall Construction Schedule.

END OF SECTION 013216