## Instructions
NPS Constructability Checklist - Instructions
Introduction - Use this checklist as a tool to inspire, document, track, and record project issues as discussed and resolved throughout preparation of Design Development (DD), Construction Documents (CD), and Request for Proposal (RFP) documents. The end result is a completed checklist identifying project issues and provides background to complete contract documents (primarily Division 1 Specifications).
Title Block - Enter Date, Park, PMIS Number (Project Management Information System), Project Title, Completed By, and if DBB or DB (Design-Bid-Build (DBB) or Design (DB)) in appropriate row.
Project Issues Column - Typical constructability issues are listed under Project Issues. Insert additional issues as needed to cover project issues not listed. If listed issue does not apply, enter N/A (not applicable). Project issues are organized to coincide with award and construction phasing of a project. They are organized under headings typically used as summary headings in a project schedule. If these project issues have significant impact on time, impacts should be shown in a projected construction schedule developed during design. This is an effective way to accomplish construction planning, develop realistic expectations, and account for time and cost implications of project issues.
Schematic Design (SD) Column - Complete necessary research to gain full understanding of project issues which will need to be considered. Explain specific issue in general for each project issue.
Design Development (DD) or Request for Proposal (RFP) Comments Column - Develop necessary in-depth research to gain full understanding of project issues which will need to be considered. Explain specific issue in general for each project issue.
Construction Documents (CD) or Request for Proposal (RFP) Resolution Column - Develop strategy on how each project issue will be resolved contractually. Indicate how it will be resolved. Refer to specification or drawing where information is contained. Be as complete as possible. Be specific with language needed to describe a constraint, requirements for specific phasing, potential impacts to cost and schedule, etc.
General - After completing this checklist, make sure resolution to project issues have been incorporated into CDs/RFPs. The Park, Project Manager (PM), and others may be responsible for some items and this should be so noted.

## Checklist
NPS Constructability Checklist
National Park Service (NPS) - Denver Service Center (DSC) ¦ 8-16-24
Date: |  | Project Title:
Park: |  | Completed By:
PMIS: |  | DBB or DB:
Item Number | Project Issues | SD Comments | DD or RFP Comments | CD or RFP Resolution
PROJECT INTRODUCTION
1 | Any non-typical contract line items. Include funding limitations, seasonal considerations, prior or concurrent work. Simply discuss constraints and concerns.
2 | Recommend contract length and seasonal breaks in contract. Identify contract timing issues and specific phasing requirements.
PERMITTING & COMPLIANCE
3 External Permit or Approval | List required government-furnished permits and approvals by agency-type. Example: USACE-CWA404 NWP18. Include contact information and phone number.
4 External Permit or Approval | List requirements for government-furnished permits. Include inspections meetings, close-out requirements, and drawings.
5 External Permit or Approval | List required Construction Contractor-furnished permits and approvals.
6 External Permit or Approval | Describe where and how permit requirements are included in design package. For each permit, describe requirement, specification (section and paragraph) and/or drawing number.
7 Internal Compliance | Identify compliance requirements: SHPO (State Historic Preservation Officer), NEPA (National Environmental Policy Act), EA (Environmental Assessment). List requirement, status, and date or expected date.
8 Internal Compliance | Complete approvals: Director's, IRB (Investment Review Board), congressional funding issues. Is estimate within available funds? Is there adequate time to complete work within project and funding constraints?
9 General | Identify required special inspections. List inspecting or approving organization and reason required. Identify construction inspections. Provide completed Construction Inspection Checklist.
STAGING & MOBILIZATION
10 | Identify areas for staging including areas for Contractors and Subcontractors, material, stockpile, refuse, and parking. Identify areas for construction camp, if applicable. List drawing number(s) showing staging area(s).
11 | Identify temporary utilities available for construction. List available utilities-electrical, phone, non-potable and potable water, sanitary-provider, meter needed, and responsible cost party.
12 | Identify construction logistics. List traffic control, access restrictions, visitor protections, work hour restrictions, bridges, features, etc.
13 | Identify impacts to park and visitor operations. List impacts to visitors, neighborhood-urban, detours, closures, etc.
14 | Identify site access issues including remote and road type constrained sites, weather closure restrictions, road and bridge load limits, road and tunnel height restrictions, crane and helicopter requirements, equipment wheel loading/track considerations, crane cribbing, etc.
SUBMITTALS
15 | List material submittals on critical path for any contracting method. List material submittals requiring government approval.
16 | List long lead items: material and equipment, availability concerns, special delivery requirements.
17 | List of sole source materials and government-furnished materials or equipment. Provide specifications addressing salient characteristic requirements per NPS DSC Workflows.
SITE LAYOUT / RESOURCE PROTECTION
18 | Types of resource protection required. List where and how requirements are included in design package.
19 | Accurate survey data on plans: BMs (Benchmarks), TBMs (Temporary Bench Marks), Topo (Topographic).
20 | Preliminary site investigation complete. Existing conditions verified, included, and addressed in submittal package.
21 | Construction limits cleary shown and defined for access, construction, visitor, wetlands consideration. List where and how requirements are included in design package.
22 | Special signage requirements: Describe and list where requirements are included in design package.
23 | List work safety concerns, location, and needs. Include height, weather, animal, aerial, public accessibility, security, confined space, pathologic, atmospheric, overwater, etc.
DEMOLITION
24 | All existing utilities located and accurately shown. Describe where shown.
25 | Temporary systems required. Identify for park or public: access, power, water, sanitary, covered access, exhibit relocation, movement assistance, accessibility, bypass, UPS (uninterruptible power supply), etc.
26 | Salvage, recycling, storage and disposal requirements: Who is removing salvageable equipment and where requirements are included in design package? Provide list, needs, delivery location if required.
27 | Describe where noise, dust, safety concerns for the public or environment are included in design package.
28 | Constraints on means and methods: Blasting, burning, tidal, weather, public accessibility, existing structures/features, holidays and seasonal, permitting, etc. Discuss concerns and known constraints. Provide resolution for final submittal.
29 | Hazardous material demo methods and disposal state and local requirements: Describe hazardous materials being addressed, how, and where in design package. Include septic and tank abandonment.
30 | Archeological monitoring requirements: Describe needs contained in design package. Identify who provides monitor.
CONSTRUCTION
31 | Material, equipment, labor availability for remote sites: Describe issues and where included in design package.
32 | Site access restrictions to construction operations if different or more substantial than items 12 and 14.
33 | Anticipated weather considerations, construction season, optimum time to advertise, recommended contract length.
34 | Park/Concession imposed restrictions included in design package and impacts on schedule and cost.
35 | Describe full scope of work for local utility companies and Construction Contractor for each utility. Provide clear information on timing, costs, drawing needs, and coordination.
36 | Describe disruption and bypass requirements for utility connections, closures, and maximum allowable interruptions. Describe where addressed in design package.
37 | Specific phasing requirements: Detail how and where provided in design package.
38 | Describe specialized materials/installation methods certifications/training requirements. Detail government-required speciality services, or inspections. List requirements.
39 | Coordination with park or concessionaire on beneficial occupancy: Grand opening, fixed completion dates, etc.
40 | Adjacent or concurrent contracts coordination / Overlaps on concurrent or future contracts.
41 | Value Engineering potential, results, issues
PROJECT CLOSEOUT
42 | Specify specialized training requirements, certifications and warranty.
43 | Operation & Maintenance (O&M) requirements: Include attic stock and specialized O&M contracts, if needed.
44 | List permits needing closure and points of contact.Describe requirement and include specification and/or drawing location for each.
45 | List long term maintenance needs and location where addressed in design package. List concerns early even if long term answers are not available.
46 | Post Construction Requirements.